## Schedule
Task No. | Task | Wanderer | Date | Status | Notes
1 | TRANSFORMATIONS
a | classify columns as "needed for model", "needed for features", or "not needed" | Phoenix | 2020-08-20 | DONE
b | "business categories" | Phoenix | 2020-08-25 | IN PROGRESS | function built and tested; need to execute code from business.json and re-paste data
c | "business attributes" | Phoenix | 2020-08-25 | IN PROGRESS
d | "business hours" | Phoenix | 2020-08-25 | IN PROGRESS | function built and tested; need to execute code from business.json and re-paste data
e | "check-in dates" | Phoenix | 2020-08-25 | IN PROGRESS | function built and tested; need to execute code from business.json and re-paste data
f | Autocorrect words in the "review text" | Yash |  | TBD
2 | EXPLORATORY ANALYSIS
a | "business city" and "business state" | Yash | 2020-08-26 | IN PROGRESS
b | "business review count" | Yash | 2020-08-26 | IN PROGRESS
c | "business attributes" |  | 2020-08-27 | BLOCKED
d | "business categories" |  | 2020-08-27 | BLOCKED
e | "business hours" |  | 2020-08-27 | BLOCKED
f | "check-in dates" |  | 2020-08-27 | BLOCKED
3 | BINARY CLASSIFIER BASELINE
a | similarity comparison for words |  | 2020-08-28 | BLOCKED
4 | CLUSTERING BASELINE
a | evaluate and explore k=2 (positive vs negative) |  | TBD | BLOCKED
5 | SEND OUT COURSERA FINANCIAL AID | Aniket | 2020-09-03 | TBD
6 | COURSES: #1, #2 | ALL | 2020-09-20 | IN PROGRESS
7 | SET UP REPOSITORY | Aniket | 2020-08-27 | IN PROGRESS

## Data Columns
Column | Requirement | Transformation
business_id | filtering | none
business_city | analysis | none
business_state | analysis | none
business_stars | analysis | none
business_review_count | analysis | none
business_attributes | analysis | n columns: unpacking
business_categories | analysis | 2 columns: keep + add general categorization
business_hours | analysis | 3 columns: # days open, earliest opening, latest closing
checkin_date | analysis | 4 columns: # of morning, afternoon, evening, total check-ins
review_id | not in scope
user_id | not in scope
review_stars | model | none
review_useful | filtering | none
review_funny | filtering | none
review_cool | filtering | none
review_text | model | m columns: break down by keywords ("m" to be tested)
review_date | filtering | none
user_name | not in scope
user_review_count | filtering | none
user_yelping_since | filtering | none
user_useful | not in scope
user_funny | not in scope
user_cool | not in scope
user_elite | not in scope
user_friends | not in scope
user_fans | not in scope
user_average_stars | filtering | none
user_num_friends | filtering | none